Scope of Work

Analysis of the Risk of Natural Disasters

CIVE 202-150

Carter Janssen, Riley Ibero, Trey Williamson, Remy Balderas Izaguirre

April 21, 2026

Project Goals:

The goal of this project is to evaluate potential bias in the FEMA National Risk Index methodology by conducting a sensitivity analysis and developing an alternative definition of risk. This analysis will be performed using Census Tract-level data for two selected states: Iowa and California. These states were selected to provide contrast between a predominantly rural state and a highly urbanized state, allowing for meaningful comparison of risk distribution. Specifically, this project aims to understand and document how risk is defined and calculated in the NRI, develop an alternative risk index using external research and datasets, compare NRI results with the proposed model to identify potential categorical bias, and communicate findings through data visualization, summary tables, and geospatial mapping.

The National Risk Index defines risk as the combination of three core components: Expected Annual Loss (EAL), Social Vulnerability (SVI), and Community Resilience (CRI).

Project Tasks:

Task 1 Data Organization and Cleaning:

Our group will download all the data for Nebraska as well as find and download the data for the two other states we will be researching. Raw datasets will be cleaned using Python. This includes handling missing values, renaming variables, formatting data types, and ensuring consistency across datasets. Data will be merged using common geographic identifiers to create a unified dataset for analysis.

Task 2 Research and Development:

The team will research and document how FEMA defines and calculates risk, including Expected Annual Loss, Social Vulnerability, and Community Resilience. The original NRI risk formula and percentile-based ranking system will be replicated using Python to ensure a baseline for comparison. Using external research and engineering judgment, the team will develop an alternative risk model. This model may adjust the weighting of EAL, SVI, and CRI or incorporate additional considerations to better reflect community impacts. The purpose is to test how sensitive risk outcomes are to changes in the definition of risk.

Task 3 Sensitivity Analysis and Comparison:

A sensitivity analysis will be performed by comparing outputs from the NRI model and the proposed model. Differences in percentile rankings and categorical ratings will be analyzed to identify potential bias in how risk is currently defined.

Task 4 Visualization and Mapping:

The team will generate at least two summary tables or figures comparing risk results between models. Visualizations will include statistical summaries (mean, max, distribution) and comparative plots. Additionally, a geospatial map will be created using GeoPandas to visualize the spatial distribution of risk across both states.

Task 5 Interpretation and report:

All results will be interpreted with attention to ethical implications, including how differences in risk definitions may impact funding allocation, disaster preparedness, and community decision making. This will be written in a report that examines what implications these differences will have on the people impacted by natural disasters and how this relates to being able to give communities FEMA funding in the future to mitigate disasters.

Project Deliverables:

| Deliverable | Description | Due Date |
| --- | --- | --- |
| All Data Files | Cleaned NHTS.csv and NGSIM.csv | 4/21/2026 |
| Gantt Chart | Provide a visual project schedule. | 4/21/2026 |
| Engineering Timesheet | Tasks, distribution of work, hours | 4/21/2026 |
| Python Notebook | Fully functional .ipynb with analysis | 4/21/2026 |
| GitHub Repository | Code, data, and README | 4/21/2026 |
| Annotated Code Document | Line-by-line explanation of code | 4/21/2026 |
| Final Report | Written technical summary and results | 4/21/2026 |
| Scope of Work | Formal project scope document | 4/21/2026 |